## Use Cases
# | Feature | Use case | Admin | Guest | User/Customer | Ticket inspector | Use case description
1 | User Access | Login | X |  | X | X | Allows users to authenticate and gain access to the system by entering their credentials.
2 |  | Change Password | X |  | X |  | Enables users to update their account password for enhanced security and account management.
3 |  | Logout | X |  | X |  | Logs the user out of the system, terminating their session and ensuring the security of their account.
4 |  | Edit Profile | X |  | X |  | Allows users to modify their profile information such as contact details and personal preferences.
5 |  | View My Tickets | X |  | X |  | Displays the list of tickets purchased by the user, providing an overview of their ticket history.
6 |  | Forgot Password | X |  | X |  | Assists users in recovering or resetting their password if they have forgotten it, typically through email verification.
7 |  | View My Ticket Detail | X |  | X |  | Provides detailed information about a specific ticket purchased by the user, including match details and seat allocation.
8 |  | View Ticket Summary | X |  | X |  | Summarizes the user's ticket purchases, providing an overview of their tickets and associated details.
9 |  | Search My Ticket | X |  | X |  | Allows users to search for specific tickets based on criteria such as match date or seat location.
10 | Common Access | View Public Match Detail | X | X | X |  | Shows detailed information about a specific match, including teams, date, and venue.
11 |  | View Public Football Club Detail | X | X | X |  | Provides detailed information about a specific football club, including roster, history, and achievements.
12 |  | View Public List Football Club | X | X | X |  | Displays a list of all football clubs available to the public, including basic information and club names.
13 |  | Search Public Football Club | X | X | X |  | Allows users to search for specific football clubs within the public listings.
14 |  | View Public List Match | X | X | X |  | Displays a list of all available matches to the public, including details like date and time.
15 |  | Search Public Match | X | X | X |  | Allows users to search for specific matches based on criteria such as date, teams, or location.
16 |  | View Public List Tournament | X | X | X |  | Displays a list of all tournaments available to the public, including details like dates and participating teams.
17 |  | Search Public Tournament | X | X | X |  | Enables users to search for specific tournaments within the public listings.
18 |  | Term & Conditions | X | X | X |  | Provides users with information on the terms and conditions of using the system.
19 |  | View Instructions For Buy Tickets | X | X | X |  | Provides users with step-by-step instructions on how to purchase tickets through the system.
20 |  | Homepage | X | X | X |  | The main landing page of the website where users can navigate to different sections of the application.
21 |  | Register | X | X | X |  | Allows users to create a new account by providing necessary personal information and setting up login credentials.
22 |  | View Public List News | X | X | X |  | Displays a list of news articles related to the system or organization, keeping users updated.
23 |  | View Policy | X | X | X |  | Provides information about the organization’s policies.
24 |  | View About Us | X | X | X |  | Provides information about the organization, including its mission, history, and contact details.
25 |  | View News Detail | X | X | X |  | Shows detailed information about a specific news article, including full text and relevant images.
26 | User Management | View List User | X |  |  |  | Displays a list of all users registered in the system, including their basic information and status.
27 |  | Search User | X |  |  |  | Allows administrators to search for specific users within the system based on criteria such as name or email.
28 |  | Export User List | X |  |  |  | Enables exporting the user list to a file format (e.g., CSV or Excel) for reporting or analysis.
29 |  | Create User | X |  |  |  | Allows administrators to create a new user account with necessary information and permissions.
30 |  | View User Detail | X |  |  |  | Provides detailed information about a specific user, including profile and activity details.
31 |  | Delete User | X |  |  |  | Allows the removal of a user account from the system, including associated data and permissions.
32 | Match Management | View List Matches | X |  |  |  | Displays a list of all matches within the system, including match details and statuses.
33 |  | Search Matches | X |  |  |  | Allows users to search for specific matches based on criteria such as date, teams, or location.
34 |  | View Matches Details | X |  |  |  | Provides detailed information about a specific match, including teams, date, and venue.
35 |  | Create Matches | X |  |  |  | Allows the creation of new match entries within the system, including all relevant details.
36 |  | Update Matches | X |  |  |  | Enables updating information of existing matches, such as date, time, and participating teams.
37 |  | Delete Matches | X |  |  |  | Allows the removal of a match from the system, including any associated data.
38 | History Purchased Management | Inspect Ticket | X |  |  |  | Provides detailed inspection of a specific ticket, including its status and history.
39 |  | View History Purchased Ticket Match Seat | X |  |  |  | Displays a list of all purchased match seat records, providing an overview of historical transactions.
40 |  | Search History Purchased Ticket Match Seat | X |  |  |  | Allows searching for specific purchase records based on criteria such as date or match.
41 |  | Export History Purchased Ticket Match Seat | X |  |  |  | Enables exporting the purchase history list for match seats to a file format for reporting or analysis.
42 |  | View History Purchased Ticket Season Seat | X |  |  |  | Provides detailed information about season seat purchases, including transaction details and seat allocation.
43 | Football Club Management | View List Football Clubs | X |  |  |  | Displays a list of all existing football clubs within the system, including basic information and status.
44 |  | Search Football Club | X |  |  |  | Allows searching for specific football clubs within the system based on criteria such as name or location.
45 |  | Create Football Club | X |  |  |  | Enables the creation of a new football club entry in the system with all necessary details.
46 |  | Update Football Club | X |  |  |  | Allows updating information of an existing football club, including roster and details.
47 |  | Delete Football Club | X |  |  |  | Enables the removal of a football club from the system, retaining data in the database.
48 | Stand Management | View List Stands | X |  |  |  | Displays a list of all stands within the system, including their names and locations.
49 |  | Search Stand | X |  |  |  | Allows searching for specific stands within the system based on criteria such as name.
50 |  | Create Stand | X |  |  |  | Enables the creation of a new stand entry in the system, including details such as name and capacity.
51 |  | Update Stand | X |  |  |  | Allows updating information of an existing stand, such as name or capacity.
52 |  | Delete Stand | X |  |  |  | Enables the removal of a stand from the system, retaining data in the database.
53 | News Management | View List News | X |  |  |  | Displays a list of all news articles in the system, including headlines and publication dates.
54 |  | Search News | X |  |  |  | Allows searching for specific news articles within the system based on criteria such as title or date.
55 |  | View News Details | X |  |  |  | Shows detailed information about a specific news article, including full text and relevant images.
56 |  | Delete News | X |  |  |  | Allows the removal of a news article from the system, including associated media and content.
57 |  | Create News | X |  |  |  | Enables the creation of a new news article entry in the system, including text and media content.
58 |  | Update News | X |  |  |  | Allows updating information of an existing news article, including text and media content.
59 | Season Management | View List Season | X |  |  |  | Displays a list of all seasons in the system, including details such as season name and duration.
60 |  | Create Season | X |  |  |  | Enables the creation of a new season entry in the system with relevant details.
61 |  | Search Season | X |  |  |  | Allows searching for specific seasons within the system based on criteria such as name or date.
62 |  | Update Season | X |  |  |  | Enables updating information of an existing season, such as name or duration.
63 |  | Delete Season | X |  |  |  | Enables the removal of a season from the system, retaining data in the database.
64 | SeatArea Management | View List SeatArea | X |  |  |  | Displays a list of all seat areas within the system, including details such as location and capacity.
65 |  | Update SeatArea | X |  |  |  | Allows updating details of seat areas, such as location and capacity.
66 |  | View List SeatClass | X |  |  |  | Displays a list of all seat classes within the system, including class names and descriptions.
67 |  | Update SeatClass | X |  |  |  | Enables updating information about seat classes, including class names and descriptions.
68 | Payment Methods | Payment Methods |  |  | X |  | Displays and manages available payment methods for processing transactions.
69 | Dashboard | Dashboard | X |  |  |  | Provides an overview of key metrics and system status, including summaries of user activity, ticket sales, and match schedules.

## Product
[9 empty] | 10% | 10% | 10% | 50% | 20% |  |  | 0.3 | 4440 | 4440
# | Feature | Screen/Function | Screen/Function Details | Complexity | Điểm | PIC | Plan |  | Status | [5 empty] | Defects | Quality | LOC |  | Note
[7 empty] | Planned | Actual | BA | SRS | SDS | Coding | UT/IT | ALL |  |  | Plan | Grade
1 | User Access | Login | Allows users to log in to the system. | Medium | 7 | Trần Anh Quân | ITER1 | ITER1 | Completed | Completed | Completed | Completed | Completed | Completed | 0 | High | 120 | 120
2 |  | Password Change | Enables users to change their account password. | Simple | 6 | Trần Anh Quân | ITER2 | ITER2 | Completed | Completed | Completed | Completed | Completed | Completed | 0 | High | 60 | 60
3 |  | Logout | Logs the user out of the system. | Simple |  | Trần Anh Quân | ITER2 | ITER2 | Completed | Completed | Completed | Completed | Completed | Completed |  | High | 60 | 60
4 |  | Edit Profile | Allows users to update their profile information. | Simple | 8 | Đỗ Tiến Thuật | ITER2 | ITER2 | Completed | Completed | Completed | Completed | Completed | Completed |  | High | 60 | 60
5 |  | View My Tickets | Displays the user's purchase history. | Simple |  | Quách Thế Kiệt | ITER3 | ITER3 | Completed | Completed | Completed | Completed | Completed | Completed |  | High | 60 | 60
6 |  | Forgot Password | Assists users in recovering a forgotten password. | Medium |  | Trần Anh Quân | ITER2 | ITER2 | Completed | Completed | Completed | Completed | Completed | Completed |  | High | 120 | 120
7 |  | View My Ticket Detail | Provides details of a specific ticket purchased. | Simple |  | Quách Thế Kiệt | ITER3 | ITER3 | Completed | Completed | Completed | Completed | Completed | Completed |  | High | 60 | 60
8 |  | View Ticket Summary |  | Simple |  | Đỗ Tiến Thuật | ITER2 | ITER2 | Completed | Completed | Completed | Completed | Completed | Completed |  | High | 60 | 60
9 |  | Search My Ticket |  | Simple |  | Quách Thế Kiệt | ITER3 | ITER3 | Completed | Completed | Completed | Completed | Completed | Completed |  | High | 60 | 60
10 | Common Access | View Public Match Detail | Shows detailed information about a particular match. | Medium |  | Đỗ Tiến Thuật | ITER2 | ITER2 | Completed | Completed | Completed | Completed | Completed | Completed |  | High | 120 | 120
11 |  | View Public Football Club Detail |  | Simple |  | Đỗ Tiến Thuật | ITER3 | ITER3 | Completed | Completed | Completed | Completed | Completed | Completed |  | High | 60 | 60
12 |  | View Public List Football Club |  | Simple |  | Đỗ Đức Vinh | ITER3 | ITER3 | Completed | Completed | Completed | Completed | Completed | Completed |  | High | 60 | 60
13 |  | Search Public Football Club |  | Simple |  | Đỗ Đức Vinh | ITER3 | ITER3 | Completed | Completed | Completed | Completed | Completed | Completed |  | High | 60 | 60
14 |  | View Public List Match | Displays a list of all matches. | Simple |  | Đỗ Đức Vinh | ITER3 | ITER3 | Completed | Completed | Completed | Completed | Completed | Completed |  | High | 60 | 60
15 |  | Search Public Match |  | Simple |  | Đỗ Đức Vinh | ITER3 | ITER3 | Completed | Completed | Completed | Completed | Completed | Completed |  | High | 60 | 60
16 |  | View Public List Season |  | Simple |  | Đỗ Đức Vinh | ITER3 | ITER3 | Completed | Completed | Completed | Completed | Completed | Completed |  | High | 60 | 60
17 |  | Search Public Season |  | Simple |  | Đỗ Đức Vinh | ITER3 | ITER3 | Completed | Completed | Completed | Completed | Completed | Completed |  | High | 60 | 60
19 |  | Term & Conditions |  | Simple |  | Trần Anh Quân | ITER1 | ITER1 | Completed | Completed | Completed | Completed | Completed | Completed |  | High | 60 | 60
19 |  | View Instructions For Buy Tickets | Provides instructions on how to purchase tickets. | Simple |  | Trần Anh Quân | ITER2 | ITER2 | Completed | Completed | Completed | Completed | Completed | Completed |  | High | 60 | 60
20 |  | Homepage | The main landing page of the web | Medium |  | Nguyễn Cảnh Dương | ITER3 | ITER3 | Completed | Completed | Completed | Completed | Completed | Completed |  | High | 120 | 120
21 |  | Register | Allows creating a new account | Medium | 7 | Trần Anh Quân | ITER1 | ITER1 | Completed | Completed | Completed | Completed | Completed | Completed | 0 | High | 120 | 120
22 |  | View Public List News | Displays a list of news. | Simple |  | Nguyễn Cảnh Dương | ITER3 | ITER3 | Completed | Completed | Completed | Completed | Completed | Completed |  | High | 60 | 60
23 |  | View Policy |  | Simple |  | Trần Anh Quân | ITER2 | ITER3 | Completed | Completed | Completed | Completed | Completed | Completed |  | High | 60 | 60
24 |  | View About Us | Provides information about the organization. | Simple |  | Trần Anh Quân | ITER2 | ITER2 | Completed | Completed | Completed | Completed | Completed | Completed |  | High | 60 | 60
25 |  | View News Detail | Shows detailed information of a specific news article. | Simple |  | Nguyễn Cảnh Dương | ITER3 | ITER3 | Completed | Completed | Completed | Completed | Completed | Completed |  | High | 60 | 60
26 | User Management | View List User | Displays a list of all users in the system. | Simple | 7 | Đỗ Đức Vinh | ITER1 | ITER1 | Completed | Completed | Completed | Completed | Completed | Completed |  | High | 60 | 60
27 |  | Search User | Allows searching for users in the system. | Simple | 7 | Đỗ Đức Vinh | ITER1 | ITER1 | Completed | Completed | Completed | Completed | Completed | Completed |  | High | 60 | 60
28 |  | Export User List | Enables exporting the user list to a file. | Simple |  | Trần Anh Quân | ITER3 | ITER3 | Completed | Completed | Completed | Completed | Completed | Completed |  | High | 60 | 60
29 |  | Create User | Allows creating a new user account. | Simple | 5 | Đỗ Đức Vinh | ITER2 | ITER2 | Completed | Completed | Completed | Completed | Completed | Completed |  | High | 60 | 60
30 |  | View User Detail | Enables updating a user's profile information. | Simple |  | Đỗ Đức Vinh | ITER2 | ITER2 | Completed | Completed | Completed | Completed | Completed | Completed |  | High | 60 | 60
31 |  | Delete User | Allows deletion of a user account. | Simple |  | Đỗ Đức Vinh | ITER2 | ITER2 | Completed | Completed | Completed | Completed | Completed | Completed |  | High | 60 | 60
32 | Match Management | View List Matches | Displays a list of all matches in the system. | Simple | 7 | Đỗ Tiến Thuật | ITER1 | ITER1 | Completed | Completed | Completed | Completed | Completed | Completed |  | High | 60 | 60
33 |  | Search Matches | Allows searching for specific matches. | Simple |  | Đỗ Tiến Thuật | ITER2 | ITER2 | Completed | Completed | Completed | Completed | Completed | Completed |  | High | 60 | 60
34 |  | View Matches Details | Shows detailed information about a specific match. | Simple |  | Đỗ Tiến Thuật | ITER2 | ITER2 | Completed | Completed | Completed | Completed | Completed | Completed |  | High | 60 | 60
35 |  | Create Matches | Allows creating a new match entry in the system. | Simple | 7 | Đỗ Tiến Thuật | ITER1 | ITER1 | Completed | Completed | Completed | Completed | Completed | Completed |  | High | 60 | 60
36 |  | Update Matches | Enables updating information of an existing match. | Simple |  | Đỗ Tiến Thuật | ITER2 | ITER2 | Completed | Completed | Completed | Completed | Completed | Completed |  | High | 60 | 60
37 |  | Delete Matches | Allows deletion of a match from the system. | Simple | 7 | Đỗ Tiến Thuật | ITER1 | ITER1 | Completed | Completed | Completed | Completed | Completed | Completed |  | High | 60 | 60
38 | History purchased Management | Inspect Ticket | Displays a list of all purchase history records. | Simple |  | Nguyễn Cảnh Dương | ITER3 | ITER3 | Completed | Completed | Completed | Completed | Completed | Completed |  | High | 60 | 60
39 |  | View History Purchased Ticket Match Seat | Shows detailed information of a specific purchase. | Simple | 5.5 | Nguyễn Cảnh Dương | ITER2 | ITER2 | Completed | Completed | Completed | Completed | Completed | Completed |  | High | 60 | 60
40 |  | Search History Purchased Ticket Match Seat | Allows searching for specific purchase records. | Simple |  | Nguyễn Cảnh Dương | ITER2 | ITER2 | Completed | Completed | Completed | Completed | Completed | Completed |  | High | 60 | 60
41 |  | Export History Purchased Ticket Match Seat |  | Simple |  | Trần Anh Quân | ITER3 | ITER3 | Completed | Completed | Completed | Completed | Completed | Completed |  | High | 60 | 60
42 |  | View history purchased ticket season seat | Allows deletion of a purchase record from the system. | Simple |  | Nguyễn Cảnh Dương | ITER2 | ITER2 | Completed | Completed | Completed | Completed | Completed | Completed |  | High | 60 | 60
43 | Football club Management | View List Football Clubs | Displays a list of all football clubs in the system. | Simple | 7 | Quách Thế Kiệt | ITER1 | ITER1 | Completed | Completed | Completed | Completed | Completed | Completed |  | High | 60 | 60
44 |  | Search Football club | Allows searching for specific football clubs. | Simple | 6 | Quách Thế Kiệt | ITER2 | ITER2 | Completed | Completed | Completed | Completed | Completed | Completed |  | High | 60 | 60
45 |  | Create Football club | Allows creating a new football club entry in the system. | Simple |  | Quách Thế Kiệt | ITER2 | ITER2 | Completed | Completed | Completed | Completed | Completed | Completed |  | High | 60 | 60
46 |  | Update Football club | Enables updating information of an existing football club. | Simple |  | Quách Thế Kiệt | ITER2 | ITER2 | Completed | Completed | Completed | Completed | Completed | Completed |  | High | 60 | 60
47 |  | Delete Football club | Allows deletion of a football club from the system. | Simple |  | Quách Thế Kiệt | ITER2 | ITER2 | Completed | Completed | Completed | Completed | Completed | Completed |  | High | 60 | 60
48 | Stand Management | View List Stands | Displays a list of all stands in the system. | Simple | 7 | Quách Thế Kiệt | ITER1 | ITER1 | Completed | Completed | Completed | Completed | Completed | Completed |  | High | 60 | 60
49 |  | Search Stand | Allows searching for specific stands. | Simple |  | Quách Thế Kiệt | ITER2 | ITER2 | Completed | Completed | Completed | Completed | Completed | Completed |  | High | 60 | 60
50 |  | Create Stand | Allows creating a new stand entry in the system. | Simple | 7 | Quách Thế Kiệt | ITER1 | ITER1 | Completed | Completed | Completed | Completed | Completed | Completed |  | High | 60 | 60
51 |  | Update Stand | Enables updating information of an existing stand. | Simple | 7 | Quách Thế Kiệt | ITER1 | ITER1 | Completed | Completed | Completed | Completed | Completed | Completed |  | High | 60 | 60
52 |  | Delete Stand | Allows deletion of a stand from the system. | Simple | 7 | Quách Thế Kiệt | ITER1 | ITER1 | Completed | Completed | Completed | Completed | Completed | Completed |  | High | 60 | 60
53 | News Management | View List News | Displays a list of all news articles in the system. | Simple | 7 | Nguyễn Cảnh Dương | ITER1 | ITER1 | Completed | Completed | Completed | Completed | Completed | Completed | 0 | High | 60 | 60
54 |  | Search News | Allows searching for specific news articles. | Simple | 7 | Nguyễn Cảnh Dương | ITER1 | ITER1 | Completed | Completed | Completed | Completed | Completed | Completed |  | High | 60 | 60
55 |  | View News Details | Shows detailed information of a specific news article. | Simple | 7 | Nguyễn Cảnh Dương | ITER1 | ITER1 | Completed | Completed | Completed | Completed | Completed | Completed |  | High | 60 | 60
56 |  | Delete News | Allows deletion of News from the system. | Simple | 7 | Nguyễn Cảnh Dương | ITER1 | ITER1 | Completed | Completed | Completed | Completed | Completed | Completed |  | High | 60 | 60
57 |  | Create News | Allows creating a new news article entry in the system. | Simple | 7 | Nguyễn Cảnh Dương | ITER1 | ITER1 | Completed | Completed | Completed | Completed | Completed | Completed |  | High | 60 | 60
58 |  | Update News | Enables updating information of an existing news article. | Simple | 7 | Nguyễn Cảnh Dương | ITER1 | ITER1 | Completed | Completed | Completed | Completed | Completed | Completed |  | High | 60 | 60
59 | Season Management | View List Season | Displays a list of all seasons in the system. | Simple | 7 | Đỗ Đức Vinh | ITER1 | ITER1 | Completed | Completed | Completed | Completed | Completed | Completed |  | High | 60 | 60
60 |  | Create Season | Allows creating a new season entry in the system. | Simple |  | Trần Anh Quân | ITER2 | ITER2 | Completed | Completed | Completed | Completed | Completed | Completed |  | High | 60 | 60
61 |  | Search Season |  | Simple |  | Trần Anh Quân | ITER2 | ITER2 | Completed | Completed | Completed | Completed | Completed | Completed |  | High | 60 | 60
62 |  | Update Season | Enables updating information of an existing season. | Simple |  | Đỗ Tiến Thuật | ITER2 | ITER2 | Completed | Completed | Completed | Completed | Completed | Completed |  | High | 60 | 60
63 |  | Delete Season | Allows deletion of a season from the system. | Simple |  | Đỗ Đức Vinh | ITER2 | ITER2 | Completed | Completed | Completed | Completed | Completed | Completed |  | High | 60 | 60
64 | SeatArea Management | View List SeatArea |  | Simple |  | Đỗ Tiến Thuật | ITER3 | ITER3 | Completed | Completed | Completed | Completed | Completed | Completed |  | High | 60 | 60
65 |  | Update SeatArea |  | Simple |  | Đỗ Tiến Thuật | ITER3 | ITER3 | Completed | Completed | Completed | Completed | Completed | Completed |  | High | 60 | 60
66 | SeatClass Management | View List SeatClass |  | Simple |  | Đỗ Tiến Thuật | ITER3 | ITER3 | Completed | Completed | Completed | Completed | Completed | Completed |  | High | 60 | 60
67 |  | Update SeatClass |  | Simple |  | Đỗ Tiến Thuật | ITER3 | ITER3 | Completed | Completed | Completed | Completed | Completed | Completed |  | High | 60 | 60
68 | Payment Methods | Payment Methods |  | Simple |  | Trần Anh Quân | ITER3 | ITER3 | Completed | Completed | Completed | Completed | Completed | Completed |  | High | 60 | 60
69 | Dashboard | Dashboard | Provides an overview of the system's status and key metrics. | Simple |  | Quách Thế Kiệt | ITER3 | ITER3 | Completed | Completed | Completed | Completed | Completed | Completed | 0 | High | 60 | 60
–Complex function/screen (>=15 screen fields, >=7 transactions): 240
–Medium one (7-15 screen fields, 3-7 transactions): 120
–Simple one (<7 screen fields, <3 transactions): 60

## MasterData
TEAM | STATUS | ITERATOR | Complexity | Quality
Đỗ Đức Vinh | New | ITER1 | Complex | High
Quách Thế Kiệt | Doing | ITER2 | Medium | Medium
Đỗ Tiến Thuật | Done | ITER3 | Simple | Low
Trần Anh Quân | ToDo
Nguyễn Cảnh Dương | Completed
|  |  | UT | IT | ST
Complexity | LOC | 26 | 7 | 4 | 2 | Lấy gấp 2 Fsoft's norm
Complex | 240 | 6.24
Medium | 120 | 3.12
Simple | 60 | 1.56
Quality
High | 100%
Medium | 75%
Low | 50%
ITERATOR | Start | End
ITER1 | 06/05/2024 | 31/05/2024 | 1 tuần đầu tháng 5 để làm BA
ITER2 | 1/06/2024 | 21/06/2024 | 1 tuần cuối tháng 5 để làm BA
ITER3 | 22/06/2024 | 12/07/2024